## Query Logs
Sr.No | Module | Team member | Area | Query | Comments / Resolution | Status | Query Raised Date | Query Resolved Date | Comments / Resolution
1 | View Contact | Chandan | Requirement | How does user distinguish between a deleted contacted and a Block contact |  | closed | 2012-11-14 |  | [TB] A deleted contact will no longer be visible to the user, while a Blocked contact will be visible and allowing a user unblock when necessary (block link much change to unblock once clicked).
2 | View Contact | Chandan | Requirement | When you say delete contact do you want me to delete the record from DB(Hard Delete) . As I dont really understand to have both delete and Block. |  | closed | 2012-11-14 |  | TB] A deleted contact must never be deleted from the database, but flagged as deleted. Delete – removes the contact from his view contact details list (This will not be deleted from DB) Blocked – still visible in view contact details list, but is disabled (a user will no longer receive inCyytes from this contact – use skype as an example)
3 | View Contact | Chandan | Requirement | I need more details on the 1.d section where is the compose page and if it just going to send mails , I think we need just the user email id or do u have any other thought ? |  | closed | 2012-11-14 |  | [TB] See (compose_new_message) under jsp/messages A message is similar to a comment/note stored in the database and will be time stamped. All users will be given a chance to alter their account settings, which will also allow the message sent to them via email if they choose.
4 | Search Section on the view contact | Chandan | Requirement | The search section on the View All contacts list doesnot contain any link or button to perfrom search.Also I see numbers 1-3 alphabets A-Z ,I understand that this might be for filtering the records .I would like to know the field in the contact data ie,firstname ,real name etc) .Also why there is no link or button next to the text box |  | open | 2012-11-19 |  | [TB] Nandkishor will need to add a search glass to the end of this search field. The Numbers/Alphabet filter is correctly used to filter the contacts in the following order Firstname, (if FirstName does not exist) username, (if username) email address
5 | Advance Search Section on the view contact | Chandan | Requirement | What should be displayed in the search result and Where ie on the same page or shall I bring the user to the View Contact page after a advanced seach is performed |  | open | 2012-11-19 |  | [TB] The Advanced search should display the list on the same page. That is, with Advanced search navigation bar still be selected but remove advanced search fields and Display List of retrieved contacts.
6 | Sending Polls to Region | Remi | Requirement | Explain the requirements to sending a Poll to a region and provide backend queries or code. |  | open | 2012-12-06 |  | [TB] 2 things to make note here... When the user selects a postcode /region AJAX should be used to retrieve the number of people tageted for the poll (to be displayed to the user). Also when sending, the pollDao will be used to retrieve the persons ID and email to send to.